## Sheet1
| Action Item | Description | Next Steps | Date Needed for 7/11 Service
Outdoor | Marking for Social Distancing | Create Circles to assist parishoners with placement of lawn chairs (BYOC) | Recruited Scott Moeller & Rob Heckert and get estimated capacity | Estimate by June 26
Outdoor | Offering | Construct two offering boxes | Recruit volunteers | Week of June 22
Outdoor | Sound system | Schedule volunteer to set up and tear down system | Recruit volunteers | Week of June 22
Outdoor | Outdoor seating | Communicate to CUMC members to BYOC for outdoor services | Send out communication | Week of June 29
Indoor & Outdoor | Greeters w/Smart phones | Schedule 2 Greeters & share updated role that includes assisting with sign in/tracking process | Develop new expanded role & recruit | Week of June 22
Indoor & Outdoor | Ushers | Schedule 2 Ushers & share updated role | Develop new expanded role & recruit | Week of June 22
Indoor & Outdoor | QR Code | Post QR codes in accessible areas & Create outdoor QR codes | Develop QR Code signs | Week of June 22
Indoor & Outdoor | Cleaning | Schedule volunteer to clean high-touch items between services when two services resume (door handes, light switches, etc) | Recruit volunteers | Week of June 22
Indoor & Outdoor | Covenant | Church Council approval of Covenant | Church council email vote | Week of June 22
Indoor & Outdoor | Volunteers | Create listing of volunteers needed | Finalize volunteer expanded duties and listing | Week of June 22
Indoor & Outdoor | Bathroom Access | Utilize only the two bathrooms on the mail level (by front door & by elevator) with building access needed through South side and include communicating "when at all possible, please use the restroom before services to minimize high-touch surfaces" | Send out communication | Week of June 29
Indoor & Outdoor | Earlier Arrival | Allow additional time to "sign in" for service for tracking and being seated with social distancing | Send out communication | Week of June 29
Indoor & Outdoor | Offering | Communicate to CUMC members new offeratory process & encourage online giving for contactless | Send out communication | Week of June 29
Indoor & Outdoor | Communication | Create videos to welcome back parishoners | Create videos | Week of June 29
Indoor & Outdoor | Communication | Create video to demonstrate "sign in" process | Create videos | Week of June 29
Indoor & Outdoor | Communication | Ask parishoners to bring smart phone to service to utilize QR Code sign in, if possible, and share Greeters will assist if where smart phones aren't available | Send out communication | Week of June 29
Indoor & Outdoor | Social Distancing | Communicate that we will not congregate at back of church or in parking lot | Send out communication | Week of June 29
Indoor & Outdoor | Covenant | Sharing of Covenant with parishoners | Send out communication | Week of June 29
Indoor & Outdoor | Scheduling | Add scheduling link to website and communicate to parishoners | Set up Scheduling tool and add to website | Week of June 29
Indoor & Outdoor | Masks | Ensure masks are available for use if needed | Secure more cloth masks & display | Week of June 29
Indoor & Outdoor | Seating | Ensure Ushers and parishoners minimize contact through seating most forward & dismissing back to front | Add to Usher expanded role
Indoor | Offering | Allow drop off of offering at beginning and end of service
Indoor | Marking for Social Distancing | Mark off pews for appropriate distancing and using alternating pews for Sat/Sun service when two services resume indoors |  | Week of July 13
Indoor | Sound system | Schedule 1 Sound Board operator/Projector | Recruit volunteers | Week of July 13
Indoor | Doors/Entrances | Ensure Greeters prop open doors to minimize contact